## S2
Task # | Module Name | RCT ID | Core Feature | Task Description | Tracking in Jira (Y/N)? | Start Date | End Date | % Progress | Task Owner
1 | 01. Account Management | 1.06 | View Audit Logs | Design audit log table with columns (UserID, Action, Entity, Timestamp) and filter options (date, user, action) | YES | 2026-03-31 | 2026-04-01 | 100% | Aditya Srivastava
2 | 01. Account Management | 1.06 | View Audit Logs | Develop backend endpoint GET /audit-logs with query filters and pagination support | YES | 2026-03-31 | 2026-04-01 | 100% | Aditya Srivastava
3 | 01. Account Management | 1.06 | View Audit Logs | Implement middleware to restrict access to Admin and Pharmacist roles (ET-In) | YES | 2026-04-01 | 2026-04-02 | 100% | Aditya Srivastava
4 | 01. Account Management | 1.06 | View Audit Logs | Verify audit log entries capture correct user actions and timestamps through test cases | NO | 2026-04-01 | 2026-04-02 | 100% | Aditya Srivastava
5 | 02. Patient and Prescriber Management | 2.04 | Create Prescriber Profile | Build prescriber form with fields (Name, NPI, Phone, Address) using controlled components | YES | 2026-04-02 | 2026-04-03 | 100% | Janvi Patel
6 | 02. Patient and Prescriber Management | 2.04 | Create Prescriber Profile | Create POST /prescribers API to store prescriber data in database | YES | 2026-04-02 | 2026-04-03 | 100% | Abu Hamaza Khan
7 | 02. Patient and Prescriber Management | 2.04 | Create Prescriber Profile | Add frontend validation for required fields and NPI format (numeric, 10 digits) (FV) | NO | 2026-04-03 | 2026-04-04 | 100% | Janvi Patel
8 | 02. Patient and Prescriber Management | 2.04 | Create Prescriber Profile | Execute test cases for valid/invalid input and confirm database persistence | YES | 2026-04-03 | 2026-04-04 | 100% | Dhruvi Andani
9 | 02. Patient and Prescriber Management | 2.05 | Fetch/Update Insurance Information | Design insurance section with fields (Provider Name, Policy Number, Group ID) | YES | 2026-04-05 | 2026-04-05 | 100% | Abu Hamza Khan
10 | 02. Patient and Prescriber Management | 2.05 | Fetch/Update Insurance Information | Develop GET/PUT /insurance API to retrieve and update patient insurance details | YES | 2026-04-05 | 2026-04-06 | 100% | Pratik Naik
11 | 02. Patient and Prescriber Management | 2.05 | Fetch/Update Insurance Information | Integrate mock/external insurance service for data retrieval simulation (Integration) | YES | 2026-04-06 | 2026-04-06 | 100% | Janvi Patel
12 | 02. Patient and Prescriber Management | 2.05 | Fetch/Update Insurance Information | Validate update scenarios and handle invalid/missing insurance data (FV) | NO | 2026-04-06 | 2026-04-07 | 100% | Shivani Kotturi
13 | 03. Prescription Processing | 3.01 | Receive Prescription | Implement service to pull prescription data from FHIR endpoint into system (MedicationRequest) | YES | 2026-04-07 | 2026-04-07 | 100% | Aditya Srivastava
14 | 03. Prescription Processing | 3.01 | Receive Prescription | Map incoming data to internal prescription schema and store in database | YES | 2026-04-07 | 2026-04-08 | 100% | Abu Hamza Khan
15 | 03. Prescription Processing | 3.01 | Receive Prescription | Display received prescriptions in “New” queue sorted by timestamp | YES | 2026-04-08 | 2026-04-08 | 100% | Pratik Naik
16 | 03. Prescription Processing | 3.01 | Receive Prescription | Test ingestion flow including duplicate handling and missing fields | NO | 2026-04-08 | 2026-04-09 | 100% | Dhruvi Andani
17 | 03. Prescription Processing | 3.02 | Review & Approve Prescription | Develop UI screen for pharmacists to review prescription details and drug selection | YES | 2026-04-09 | 2026-04-09 | 100% | Janvi Patel
18 | 03. Prescription Processing | 3.02 | Review & Approve Prescription | Create PUT /prescriptions/{id}/approve endpoint to update status to “Ready” | YES | 2026-04-09 | 2026-04-10 | 100% | Aditya Srivastava
19 | 03. Prescription Processing | 3.02 | Review & Approve Prescription | Enforce role validation allowing only Pharmacist to approve prescriptions (ET-In) | YES | 2026-04-10 | 2026-04-10 | 100% | Abu Hamza Khan
20 | 03. Prescription Processing | 3.02 | Review & Approve Prescription | Validate status transition logic (New → In Process → Ready) through test scenarios | YES | 2026-04-10 | 2026-04-11 | 100% | Shivani Kotturi
21 | 03. Prescription Processing | 3.03 | Enter Prescription | Design manual prescription entry form with patient, drug, dosage, and quantity fields | YES | 2026-04-11 | 2026-04-11 | 100% | Pratik Naik
22 | 03. Prescription Processing | 3.03 | Enter Prescription | Implement POST /prescriptions API to save manually entered prescriptions | YES | 2026-04-11 | 2026-04-12 | 100% | Janvi Patel
23 | 03. Prescription Processing | 3.03 | Enter Prescription | Validate required inputs and numeric constraints for dosage and quantity (FV) | NO | 2026-04-12 | 2026-04-12 | 100% | Dhruvi Andani
24 | 03. Prescription Processing | 3.03 | Enter Prescription | Test manual entry flow and confirm linkage with patient and drug records | NO | 2026-04-12 | 2026-04-13 | 100% | Shivani Kotturi
25 | 04. Inventory management | 4.02 | View / Update Stock | Create inventory dashboard displaying drug name, quantity, lot number, and expiry date | YES | 2026-04-13 | 2026-04-13 | 100% | Abu Hamza Khan
26 | 04. Inventory management | 4.02 | View / Update Stock | Develop GET/PUT /inventory APIs for stock retrieval and updates | YES | 2026-04-13 | 2026-04-14 | 100% | Pratik Naik
27 | 04. Inventory management | 4.02 | View / Update Stock | Restrict stock update functionality to authorized roles (Technician/Admin) (ET-In) | YES | 2026-04-14 | 2026-04-14 | 100% | Janvi Patel
28 | 04. Inventory management | 4.02 | View / Update Stock | Test stock update scenarios including boundary values (0, negative, large quantities) | NO | 2026-04-14 | 2026-04-15 | 100% | Dhruvi Andani
29 | 04. Inventory management | 4.04 | Track Expiration Date | Extend inventory database schema to include expiration date per lot number | YES | 2026-04-15 | 2026-04-15 | 100% | Aditya Srivastava
30 | 04. Inventory management | 4.04 | Track Expiration Date | Display expiration dates and highlight items expiring within 30 days in UI | YES | 2026-04-15 | 2026-04-16 | 100% | Siyi Liu
31 | 04. Inventory management | 4.04 | Track Expiration Date | Validate date inputs and prevent past expiration dates during entry (FV) | NO | 2026-04-16 | 2026-04-16 | 100% | Shivani Kotturi
32 | 04. Inventory management | 4.04 | Track Expiration Date | Test expiry tracking logic and UI highlighting behavior | NO | 2026-04-16 | 2026-04-17 | 100% | Dhruvi Andani
33 | 04. Inventory management | 4.05 | Generate Low Stock Alert | Define threshold logic (e.g., quantity < minimum level) in backend service | YES | 2026-04-17 | 2026-04-17 | 100% | Abu Hamza Khan
34 | 04. Inventory management | 4.05 | Generate Low Stock Alert | Implement background job/service to evaluate stock levels and generate alerts | YES | 2026-04-17 | 2026-04-18 | 100% | Pratik Naik
35 | 04. Inventory management | 4.05 | Generate Low Stock Alert | Display low stock alerts in dashboard with visual indicators | YES | 2026-04-18 | 2026-04-18 | 100% | Sonali Tokala
36 | 04. Inventory management | 4.05 | Generate Low Stock Alert | Test alert triggering logic under different stock conditions | NO | 2026-04-18 | 2026-04-19 | 100% | Shivani Kotturi

## S3
Task # | Module Name | RCT ID | Core Feature | Task Description | Tracking in Jira (Y/N)? | Start Date | End Date | % Progress | Task Owner
1 | 03. Prescription Processing | 3.04 | Complete Pickup | Implement pickup status update to mark prescriptions as completed | YES | 2026-04-23 | 2026-04-24 | 0% | Abu Hamaza Khan
2 | 03. Prescription Processing | 3.04 | Complete Pickup | Build pickup confirmation UI for staff to finalize transactions | NO | 2026-04-23 | 2026-04-25 | 0% | Janvi Patel
3 | 03. Prescription Processing | 3.04 | Complete Pickup | Generate receipt after successful pickup for record keeping | NO | 2026-04-24 | 2026-04-25 | 0% | Pratik Naik
4 | 03. Prescription Processing | 3.04 | Complete Pickup | Test end-to-end pickup workflow and status transitions | NO | 2026-04-25 | 2026-04-25 | 0% | Dhruvi Andani
5 | 03. Prescription Processing | 3.04 | Complete Pickup | Produce test design and test case specification | YES | 2026-04-24 | 2026-04-25 | 0% | Shivani Kotturi
6 | 04. Inventory Management | 4.03 | Track Lot Number | Extend inventory schema to store lot numbers and expiration dates | NO | 2026-04-26 | 2026-04-27 | 0% | Aditya Srivastava
7 | 04. Inventory Management | 4.03 | Track Lot Number | Implement lot selection during dispensing to ensure traceability | YES | 2026-04-26 | 2026-04-28 | 0% | Abu Hamaza Khan
8 | 04. Inventory Management | 4.03 | Track Lot Number | Update inventory decrement logic based on selected lot numbers | NO | 2026-04-27 | 2026-04-28 | 0% | Pratik Naik
9 | 04. Inventory Management | 4.03 | Track Lot Number | Test lot tracking accuracy and expiration validation | NO | 2026-04-28 | 2026-04-28 | 0% | Shivani Kotturi
10 | 04. Inventory Management | 4.03 | Track Lot Number | Produce test design and test case specification | YES | 2026-04-27 | 2026-04-29 | 0% | Dhruvi Andani
11 | 05. Billing and Payment | 5.01 | Generate Invoice | Build invoice generation API to create invoices linked with prescriptions and patients | YES | 2026-04-29 | 2026-04-30 | 0% | Janvi Patel
12 | 05. Billing and Payment | 5.01 | Generate Invoice | Create invoice UI to preview, download, and print invoices | NO | 2026-04-29 | 2026-05-01 | 0% | Abu Hamaza Khan
13 | 05. Billing and Payment | 5.01 | Generate Invoice | Calculate totals including drug cost, taxes, and additional fees | NO | 2026-04-30 | 2026-05-01 | 0% | Pratik Naik
14 | 05. Billing and Payment | 5.01 | Generate Invoice | Test invoice creation, calculations, and data consistency | NO | 2026-05-01 | 2026-05-01 | 0% | Sonali Sri Yadav Tokala
15 | 05. Billing and Payment | 5.01 | Generate Invoice | Produce test design and test case specification | YES | 2026-04-29 | 2026-05-01 | 0% | Dhruvi Andani
16 | 05. Billing and Payment | 5.02 | Verify Payment | Implement payment verification logic to validate transactions from the payment gateway | NO | 2026-05-02 | 2026-05-03 | 0% | Aditya Srivastava
17 | 05. Billing and Payment | 5.02 | Verify Payment | Build payment status UI to display pending, completed, and failed payments | NO | 2026-05-02 | 2026-05-04 | 0% | Abu Hamaza Khan
18 | 05. Billing and Payment | 5.02 | Verify Payment | Handle failed and partial payments with proper error handling | NO | 2026-05-03 | 2026-05-04 | 0% | Janvi Patel
19 | 05. Billing and Payment | 5.02 | Verify Payment | Test different payment verification scenarios and edge cases | NO | 2026-05-04 | 2026-05-04 | 0% | Dhruvi Andani
20 | 05. Billing and Payment | 5.02 | Verify Payment | Produce test design and test case specification | YES | 2026-05-03 | 2026-05-04 | 0% | Shivani Kotturi
21 | 05. Billing and Payment | 5.03 | Payment Processing | Integrate payment gateway (e.g., Stripe) for secure transaction handling | YES | 2026-05-05 | 2026-05-06 | 0% | Pratik Naik
22 | 05. Billing and Payment | 5.03 | Payment Processing | Implement transaction processing service for handling payment flows | NO | 2026-05-05 | 2026-05-07 | 0% | Abu Hamaza Khan
23 | 05. Billing and Payment | 5.03 | Payment Processing | Build payment UI for users to submit and confirm payments | NO | 2026-05-06 | 2026-05-07 | 0% | Janvi Patel
24 | 05. Billing and Payment | 5.03 | Payment Processing | Test successful and failed payment scenarios | NO | 2026-05-07 | 2026-05-07 | 0% | Shivani Kotturi
25 | 05. Billing and Payment | 5.03 | Payment Processing | Produce test design and test case specification | YES | 2026-05-05 | 2026-05-07 | 0% | Janvi Patel
26 | 05. Billing and Payment | 5.07 | Manage Subscription Plan | Implement subscription plan logic including plan selection and upgrades | NO | 2026-05-08 | 2026-05-09 | 0% | Nidhi Pandya
27 | 05. Billing and Payment | 5.07 | Manage Subscription Plan | Build UI for managing subscription plans and viewing details | NO | 2026-05-08 | 2026-05-10 | 0% | Khushi Vithalani
28 | 05. Billing and Payment | 5.07 | Manage Subscription Plan | Handle billing cycles for monthly or yearly subscriptions | NO | 2026-05-09 | 2026-05-10 | 0% | Siyi Liu
29 | 05. Billing and Payment | 5.07 | Manage Subscription Plan | Test subscription lifecycle including upgrades and renewals | NO | 2026-05-11 | 2026-05-11 | 0% | Sonali Sri Yadav Tokala
30 | 05. Billing and Payment | 5.07 | Manage Subscription Plan | Produce test design and test case specification