## Road Map
RxFlow
|  |  | SPRINT 1 | SPRINT 2 | SPRINT 3
Application Modules | Feature Backlog | Story Points | SPRINT1 - 03-24-2026 | SPRINT2 - 04-21-2026 | SPRINT3 - 05-12-2026
01. Account Management | 01.01 Sign Up | 3 | X
| 01.02 Reset Password | 2 | X
| 01.03 Log In | 3 | X
| 01.04 Log Out | 2 | X
| 01.05 Update Profile | 4 | X
| 01.06 View Audit Logs | 3 |  | X
02. Patient and Prescriber Management | 02.01 Create Patient Profile | 3 | X
| 02.02 Update Patient Profile | 3 | X
| 02.03 Search Patient Records | 2 | X
| 02.04 Create Prescriber Profile | 3 |  | X
| 02.05 Fetch/Update Insurance Information | 4 |  | X
03. Prescription Processing | 03.01 Receive Prescription | 3 |  | X
| 03.02 Review & approved prescription | 3 |  | X
| 03.03 Enter Prescription | 3 |  | X
| 03.04 Complete Pickup | 2 |  |  | X
04. Inventory management | 04.01 Add Drug Inventory | 3 | X
| 04.02 View / Update Stock | 3 |  | X
| 04.03 Track Lot Number | 4 |  |  | X
| 04.04 Track Expiration Date | 2 |  | X
| 04.05 Generate Low Stock Alert | 2 |  | X
05. Billing and Payment | 05.01 Generate Invoice | 4 |  |  | X
| 05.02 Verify Payment | 3 |  |  | X
| 05.03 Payment Processing | 3 |  |  | X
| 05.04 Apply Discount | 3
| 05.05 Generate Billing Report | 3
| 05.06 Generate Operational Reports | 3
| 05.07 Manage Subscription Plan | 3 |  |  | X
|  | VELOCITY: | 25 | 26 | 19

## Jira Road Map S1
Timeline/Roadmap View: Weeks
Kanban Board

## Jira Road Map S2
Timeline/Roadmap View: Months
Timeline/Roadmap View: Weeks
Kanban Board

## Jira Road Map S3
Timeline/Roadmap View: Months
Timeline/Roadmap View: Weeks
Kanban Board